## Overview
MediaDotGames — Project Plan
Synced from Jira • March 12, 2026
Project Summary
Total Tasks | 101
Done | 19
In Progress | 8
In Review | 15
On Deck | 17
To Do | 42
Completion | 19%
Workstream Breakdown
Workstream | Epic | Total | Done | Active | To Do
Ingestion Pipeline | MDG-44 | 10 | 3 | 4 | 3
Enrichment Pipeline | MDG-45 | 12 | 3 | 8 | 1
Policy Engine | MDG-46 | 7 | 0 | 0 | 7
Data Science | MDG-47 | 14 | 3 | 8 | 3
ML | MDG-48 | 7 | 0 | 5 | 2
Source Integration | MDG-49 | 10 | 2 | 2 | 6
Frontend | MDG-50 | 7 | 0 | 1 | 6
Infrastructure & DevOps | MDG-51 | 14 | 1 | 3 | 10
Product Management | MDG-52 | 10 | 3 | 5 | 2
Documentation | MDG-53 | 10 | 4 | 4 | 2

## Project Plan
MDG Project Plan — Full Task List
Source of truth: Jira • Snapshot: March 12, 2026
Workstream | Work Item | Type | Jira Key | Status | Assignee
Ingestion Pipeline |  |  | MDG-44 | 3/10 done
Ingestion Pipeline | Remove headlines table | Task | MDG-37 | In Progress | Jesse Mazur
Ingestion Pipeline | Add 2 columns to pipeline_runs table (run_type, nth_run) | Task | MDG-38 | In Progress
Ingestion Pipeline | Add error handling to collector | Task | MDG-42 | On deck
Ingestion Pipeline | Backfill articles with newsapi's optional metadata | Task | MDG-43 | On deck
Ingestion Pipeline | Add ingestion monitoring and alerting | Task | MDG-55 | To Do
Ingestion Pipeline | Document ingestion pipeline runbook | Task | MDG-58 | To Do
Ingestion Pipeline | Spot check WaPo feed completeness | Task | MDG-60 | To Do
Ingestion Pipeline | Create newsapi-ai_headlines table | Task | MDG-32 | Done
Ingestion Pipeline | Create newsapi-ai_headlines ingestion pipeline | Task | MDG-33 | Done
Ingestion Pipeline | seed newsapi-ai-headlines table with 2 weeks of data | Task | MDG-34 | Done
Enrichment Pipeline |  |  | MDG-45 | 3/12 done
Enrichment Pipeline | Build enrichment pipeline | Task | MDG-35 | In Progress
Enrichment Pipeline | Implement Stage 1: Story Selection | Task | MDG-59 | In review
Enrichment Pipeline | Implement Stage 2: Validation & Embedding | Task | MDG-61 | In review
Enrichment Pipeline | Implement Stage 3: Deduplication | Task | MDG-62 | In review
Enrichment Pipeline | Implement Stage 5: Cluster Labeling | Task | MDG-63 | In review
Enrichment Pipeline | Implement Stage 6: Public Interest Evaluation | Task | MDG-64 | In review
Enrichment Pipeline | Implement Stage 7: Scope Classification | Task | MDG-65 | In review
Enrichment Pipeline | Implement Stage 8: Refresh enriched_headlines | Task | MDG-66 | On deck
Enrichment Pipeline | Add pipeline run logging and metrics | Task | MDG-67 | To Do
Enrichment Pipeline | LLM prompt pilot | Task | MDG-16 | Done | Paul Renshaw
Enrichment Pipeline | Design clustering logic | Task | MDG-29 | Done
Enrichment Pipeline | End-to-end pipeline integration test | Task | MDG-68 | Done
Policy Engine |  |  | MDG-46 | 0/7 done
Policy Engine | Design scoring system for "Leaderboard" | Task | MDG-18 | To Do
Policy Engine | Design policy engine rule framework | Task | MDG-69 | To Do
Policy Engine | Implement coverage omission detection | Task | MDG-70 | To Do
Policy Engine | Implement saturation detection | Task | MDG-71 | To Do
Policy Engine | Implement political asymmetry alerting | Task | MDG-72 | To Do
Policy Engine | Implement geographic asymmetry alerting | Task | MDG-73 | To Do
Policy Engine | Policy engine output storage and API | Task | MDG-74 | To Do
Data Science |  |  | MDG-47 | 3/14 done
Data Science | Define news-to-noise ratio methodology | Task | MDG-81 | In Progress
Data Science | Add media bias ratings | Task | MDG-39 | In review
Data Science | Define outlet_bias_scores composite methodology | Task | MDG-75 | In review
Data Science | Create enriched_headlines denormalized table design | Task | MDG-76 | In review
Data Science | Define heatmap metrics (v_heatmap specification) | Task | MDG-77 | In review
Data Science | Define asymmetry metrics (v_heatmap_asymmetry spec) | Task | MDG-78 | In review
Data Science | Create analytics views (v_heatmap, v_heatmap_asymmetry) | Task | MDG-79 | In review
Data Science | Figure out how to handle story aging/time windows | Task | MDG-122 | On deck
Data Science | Design ranking algorithm (multi-dimensional story sorting) | Task | MDG-80 | To Do
Data Science | Define outlet vs channel taxonomy | Task | MDG-82 | To Do
Data Science | Open questions backlog and research tracker | Task | MDG-83 | To Do
Data Science | Create a headlines dataset; pilot APIs | Task | MDG-15 | Done | Jesse Mazur
Data Science | Create initial outlets DB | Task | MDG-21 | Done | Paul Renshaw
Data Science | Figure out how to store in DB | Task | MDG-9 | Done
ML |  |  | MDG-48 | 0/7 done
ML | Set up local inference pipeline | Task | MDG-90 | In Progress
ML | Evaluate and select embedding model | Task | MDG-84 | On deck
ML | Build PI ground truth labeling dataset | Task | MDG-85 | On deck
ML | PI confidence calibration and threshold tuning | Task | MDG-87 | On deck
ML | Build model evaluation framework | Task | MDG-88 | On deck
ML | Figure out how to train datasets | Task | MDG-8 | To Do
ML | Explore fine-tuning for domain-specific performance | Task | MDG-89 | To Do
Source Integration |  |  | MDG-49 | 2/10 done
Source Integration | Add three right outlets to MVP | Task | MDG-40 | In review | Jesse Mazur
Source Integration | Write a query to find regulations.gov anomalies | Task | MDG-24 | On deck
Source Integration | Expand outlet coverage to full 14 tracked outlets | Task | MDG-91 | To Do
Source Integration | Build integration for full video transcript extraction | Task | MDG-92 | To Do
Source Integration | Research trending signal sources (X, Facebook, TikTok) | Task | MDG-93 | To Do
Source Integration | Evaluate 3rd-party trending data providers | Task | MDG-94 | To Do
Source Integration | Build trending signal ingestion pipeline | Task | MDG-95 | To Do
Source Integration | Evaluate additional news API sources | Task | MDG-96 | To Do
Source Integration | Scrape regulations.gov | Task | MDG-12 | Done | Jesse Mazur
Source Integration | Create Initial Unit Test for Scraper | Task | MDG-4 | Done | Jesse Mazur
Frontend |  |  | MDG-50 | 0/7 done
Frontend | Front end design | Task | MDG-17 | On deck | Paul Renshaw
Frontend | Design fe-api endpoints for frontend consumption | Task | MDG-100 | To Do
Frontend | Build frontend application shell | Task | MDG-101 | To Do
Frontend | News-to-noise ratio visualization | Task | MDG-102 | To Do
Frontend | Set up Grafana instance and data source connections | Task | MDG-97 | To Do
Frontend | Build heatmap dashboard in Grafana | Task | MDG-98 | To Do
Frontend | Build asymmetry dashboard in Grafana | Task | MDG-99 | To Do
Infrastructure & DevOps |  |  | MDG-51 | 1/14 done
Infrastructure & DevOps | Pipeline orchestration and scheduling | Task | MDG-109 | In Progress
Infrastructure & DevOps | Investigate hardware needs | Task | MDG-31 | On deck
Infrastructure & DevOps | Migrate billing to mdg credit card | Task | MDG-36 | On deck
Infrastructure & DevOps | Schema migration framework setup | Task | MDG-103 | To Do
Infrastructure & DevOps | pgvector extension setup and optimization | Task | MDG-104 | To Do
Infrastructure & DevOps | Build enriched_headlines table and refresh pipeline | Task | MDG-105 | To Do
Infrastructure & DevOps | Create analytics views in database | Task | MDG-106 | To Do
Infrastructure & DevOps | Database indexing strategy and optimization | Task | MDG-107 | To Do
Infrastructure & DevOps | Connection pooling setup (PgBouncer or similar) | Task | MDG-108 | To Do
Infrastructure & DevOps | CI/CD pipeline setup | Task | MDG-110 | To Do
Infrastructure & DevOps | Structured logging implementation | Task | MDG-111 | To Do
Infrastructure & DevOps | Monitoring and alerting setup | Task | MDG-112 | To Do
Infrastructure & DevOps | Configure Github Repo to protect master branch | Task | MDG-6 | To Do | Jesse Mazur
Infrastructure & DevOps | Create free tier AWS account | Task | MDG-23 | Done | Jesse Mazur
Product Management |  |  | MDG-52 | 3/10 done
Product Management | PRD review | Task | MDG-25 | In Progress
Product Management | Define MVP scope and success criteria | Task | MDG-113 | In review
Product Management | Park social media accounts | Task | MDG-20 | In review | Paul Renshaw
Product Management | Expense management and budget tracking | Task | MDG-115 | On deck
Product Management | User research and feedback loop setup | Task | MDG-117 | On deck
Product Management | Legal entity and business structure setup | Task | MDG-114 | To Do
Product Management | Go-to-market strategy development | Task | MDG-116 | To Do
Product Management | Write a PRD | Task | MDG-3 | Done | Paul Renshaw
Product Management | business plan | Task | MDG-30 | Done
Product Management | Register media dot games | Task | MDG-5 | Done
Documentation |  |  | MDG-53 | 4/10 done
Documentation | Maintain and update context repo documentation | Task | MDG-119 | In Progress
Documentation | Create user-facing methodology documentation | Task | MDG-118 | On deck
Documentation | Establish decision log and ADRs | Task | MDG-120 | On deck
Documentation | Build testing framework and quality assurance plan | Task | MDG-121 | On deck
Documentation | Integrate Jira with Cursor and establish a work flow | Task | MDG-13 | To Do
Documentation | Integrate cursor with mobile and establish ssh or similar | Task | MDG-14 | To Do
Documentation | Set up epics | Task | MDG-10 | Done
Documentation | Determine initial folder structure for project | Task | MDG-11 | Done
Documentation | Set up cursor with AI Assistant Context and rules | Task | MDG-19 | Done | Jesse Mazur
Documentation | Move newsapi.ai calls to postman | Task | MDG-22 | Done